## Summary
Agentic AI Chatbot — Future Enhancements Todo List
Generated on | 2026-09-18
Project | agentic-ai-chatbot
GitHub | https://github.com/manasa123104/agentic-ai-chatbot
Total items | 40
Priority | Count | Effort | Count
High | 17 | S (Small) | 12
Medium | 17 | M (Medium) | 20
Low | 6 | L (Large) | 8
Category | Count
API | 2
Auth / Security | 3
Big Site | 3
Chat UX | 4
Core Pipeline | 4
Data / Persistence | 1
DevOps | 3
Docs | 2
LLM | 3
Product | 2
Quality | 2
Site Editor | 3
Testing Bots | 4
UI Generator | 4
How to use
1. Open the 'Future Enhancements' sheet.
2. Filter by Priority / Category / Status using the header dropdowns.
3. Update Status (Todo → In Progress → Done) as you complete items.
4. Start with High + Small/Medium items for quick wins (FE-009, FE-018, FE-021, FE-030).
5. Tackle Large items (CRUD generator, real OAuth, self-healing) as milestone features.

## Future Enhancements
ID | Category | Enhancement | Description | Priority | Effort (S/M/L) | Status | Suggested Owner | Dependencies | Acceptance Criteria | Notes
FE-001 | Core Pipeline | Persist pipeline run history | Save every user story, bot logs, and generated file paths to a local DB or JSON store so users can reopen past runs. | High | M | Todo | Backend | None | User can list past runs and reopen any result from chat UI | Useful for demos and debugging
FE-002 | Core Pipeline | Parallel bot execution where safe | Run Bot 2 (unit) and Bot 3 (functional) in parallel after Bot 1 finishes generation. | Medium | M | Todo | Backend | FE-001 optional | Total pipeline time reduced vs sequential on multi-core machines | Keep Bot 1 sequential
FE-003 | Core Pipeline | Incremental regeneration | Allow regenerating only UI, only tests, or only one page without wiping the whole generated-app. | High | L | Todo | Backend | None | User can choose regenerate UI / unit / functional independently | Avoids losing manual edits
FE-004 | Core Pipeline | Story clarification chat | If story is vague, ask 2–3 clarifying questions in the chatbot before generating. | High | M | Todo | Full stack | LLM optional | Ambiguous stories trigger clarifying Q&A then generation | Improves output quality
FE-005 | UI Generator | Component library templates | Add reusable header/nav/footer/form/card components so generated sites share consistent design tokens. | High | M | Todo | Frontend gen | None | Generated pages reuse shared partials and CSS variables | Reduces template duplication
FE-006 | UI Generator | Responsive + accessibility defaults | Ensure generated HTML includes ARIA labels, keyboard focus styles, and mobile breakpoints. | High | M | Todo | Frontend gen | FE-005 | Lighthouse a11y score > 90 on sample pages | WCAG-oriented
FE-007 | UI Generator | Image / asset pipeline | Support uploading brand images or fetching placeholder assets into generated pages automatically. | Medium | M | Todo | Full stack | Site editor | Uploaded logo appears across generated pages | Extend current image editing
FE-008 | UI Generator | Multi-theme packs | Offer theme packs (Google-like, corporate blue, ecommerce, SaaS dark) selectable before generation. | Medium | M | Todo | Frontend gen | FE-005 | User picks theme; all pages follow pack | Beyond current color/font editor
FE-009 | Big Site | Sitemap + route map UI | Show a visual sitemap of generated multi-page sites with clickable preview links. | High | S | Todo | Frontend | BigSiteTemplates | Chat shows page list with /site/* links after big-site generation | Helps discoverability
FE-010 | Big Site | Cross-page data consistency | Shared nav labels, footer, and brand colors applied across all generated pages automatically. | High | M | Todo | Frontend gen | FE-005 | Changing brand once updates all pages | Partial today via SiteStyle
FE-011 | Big Site | CRUD page generator | From a story about products/users, generate list + create + edit + detail pages wired together. | High | L | Todo | Backend + gen | StoryAnalyzer | Story mentioning entities creates 4 related pages + controller routes | Major feature
FE-012 | Testing Bots | Auto-run tests in chatbot UI | After generation, run Maven tests and stream pass/fail summary into chat bubbles. | High | M | Todo | Backend | scripts | Chat shows green/red test summary with failing method names | Currently mostly offline scripts
FE-013 | Testing Bots | Coverage report generation | Produce JaCoCo HTML coverage report for generated unit tests and link it from the UI. | Medium | M | Todo | Backend | FE-012 | Coverage % shown after test run | Nice for demos
FE-014 | Testing Bots | Playwright / Selenium functional suite | Upgrade Bot 3 from MockMvc-style checks to real browser E2E tests for multi-page flows. | Medium | L | Todo | QA eng | FE-012 | Login → dashboard → settings flow passes in headless browser | Higher fidelity
FE-015 | Testing Bots | Flaky test detection | Retry failing functional tests once and flag flaky cases in the report. | Low | S | Todo | Backend | FE-012 | Report distinguishes hard fail vs flaky | Quality of life
FE-016 | Auth / Security | Real Google OAuth2 login | Replace demo Google sign-in with Spring Security OAuth2 client using client ID/secret. | High | M | Todo | Backend | Google Cloud project | Users can sign in with real Google account and see profile email | Currently demo-oriented
FE-017 | Auth / Security | Role-based access for generated apps | Generate Spring Security config with USER/ADMIN roles from stories that mention permissions. | Medium | L | Todo | Backend gen | FE-016 | Admin-only routes return 403 for USER role | Story-aware security
FE-018 | Auth / Security | Secrets management | Move API keys fully to env/.env with validation warnings in UI when missing. | High | S | Todo | Backend | None | UI warns if OPENAI_API_KEY missing; never commits secrets | .env.example already exists
FE-019 | Chat UX | Streaming agent progress | Stream Bot 1/2/3 step logs live (SSE/WebSocket) instead of waiting for full pipeline completion. | High | M | Todo | Full stack | None | User sees live step cards while pipeline runs | Better perceived speed
FE-020 | Chat UX | Example story gallery | Add curated innovative story cards (banking, hospital, travel, learning) that one-click fill the prompt. | Medium | S | Todo | Frontend | None | At least 8 examples launch generation correctly | Marketing + onboarding
FE-021 | Chat UX | Export generated site ZIP | One-click download of generated-app as ZIP from the chat UI. | High | S | Todo | Backend | None | ZIP contains controllers, templates, tests, pom | Easy handoff
FE-022 | Chat UX | Inline page preview iframe | Embed /site preview beside chat so users see pages without leaving the chatbot. | Medium | M | Todo | Frontend | GeneratedSiteController | Preview updates after generation and style edits | Split-pane UX
FE-023 | Site Editor | Undo / redo style changes | History stack for colors, fonts, footer, and images. | Medium | M | Todo | Frontend | SiteStyleService | Ctrl+Z restores previous style snapshot | Editor polish
FE-024 | Site Editor | Live CSS custom properties panel | Expose spacing, radius, and shadow tokens in editor, not only colors/fonts. | Medium | M | Todo | Frontend | FE-005 | Changing radius updates all generated components | Design system feel
FE-025 | Site Editor | Per-page content editor | Edit headings, body copy, and CTA text per page without regenerating from story. | High | L | Todo | Full stack | Big site | User edits Home headline; other pages unchanged | Content CMS-lite
FE-026 | LLM | Provider switch (OpenAI / Azure / local) | Support OpenAI, Azure OpenAI, and local Ollama endpoints from config UI. | Medium | M | Todo | Backend | LlmClient | User selects provider; generation works offline with Ollama | Flexibility
FE-027 | LLM | Prompt quality scoring | Score story quality and suggest improvements before generation. | Low | S | Todo | Backend | LLM optional | Score 1–10 shown with tips | Helps beginners
FE-028 | LLM | Self-healing failed generation | If compilation/tests fail, feed errors back to LLM and retry generation once. | High | L | Todo | Backend | FE-012, LLM | Failed compile triggers one automatic repair pass | Agentic loop
FE-029 | DevOps | Dockerize chatbot + generated apps | Provide Dockerfile and docker-compose for one-command local/demo deploy. | Medium | M | Todo | DevOps | None | docker compose up serves UI on 8080 | Easier sharing
FE-030 | DevOps | CI pipeline for main project | GitHub Actions: build, unit test, and smoke-test pipeline API on every PR. | High | S | Todo | DevOps | GitHub repo | PR checks must pass before merge | Repo already on GitHub
FE-031 | DevOps | Publish generated app as deployable artifact | Optional button to push generated-app to a new GitHub repo or GitHub Pages. | Medium | L | Todo | Full stack | gh auth | One click creates repo and pushes generated site | Wow-factor demo
FE-032 | Data / Persistence | SQLite or H2 for styles & history | Replace in-memory SiteStyle and logs with durable storage. | Medium | M | Todo | Backend | FE-001 | Restart keeps styles and history | Production readiness
FE-033 | API | OpenAPI / Swagger docs | Expose Swagger UI for /api/pipeline and related endpoints. | Low | S | Todo | Backend | None | Swagger available at /swagger-ui.html | Developer experience
FE-034 | API | Webhook after pipeline complete | POST results JSON to a user-configured webhook URL when generation finishes. | Low | S | Todo | Backend | FE-001 | Webhook receives success payload with file list | Integrations
FE-035 | Docs | Architecture diagram + agent sequence | Add Mermaid sequence diagram of Bot1→Bot2→Bot3 to README. | Medium | S | Todo | Docs | None | README shows clear agent flow | Onboarding
FE-036 | Docs | Video demo script / sample walkthrough | Short walkthrough: innovative prompt → big site → edit style → Google login → tests. | Low | S | Todo | Docs | None | 5–7 step demo script checked into docs/ | For presentations
FE-037 | Product | Multi-user workspaces | Support multiple named projects/workspaces instead of single generated-app folder. | Medium | L | Todo | Full stack | FE-032 | User can switch between Project A and Project B | Scales beyond demo
FE-038 | Product | Prompt templates marketplace | Save/share successful user stories as templates others can reuse. | Low | M | Todo | Full stack | FE-020 | User can save current story as template | Community feature
FE-039 | Quality | Golden-story regression suite | Maintain 10 golden user stories; assert generated routes/pages/tests exist. | High | M | Todo | QA | FE-030 | CI fails if golden stories regress | Protects quality
FE-040 | Quality | Generated code linting | Run Checkstyle/Spotless on generated Java and HTML validators on templates. | Medium | S | Todo | Backend | None | Invalid HTML or style violations fail Bot 1 | Cleaner output

## Quick Wins
ID | Enhancement | Priority | Effort | Why start here
FE-009 | Sitemap + route map UI | High | S | Makes multi-page sites discoverable immediately
FE-018 | Secrets management polish | High | S | Security hygiene with low effort
FE-021 | Export generated site ZIP | High | S | Great demo handoff feature
FE-030 | GitHub Actions CI | High | S | Protects the public GitHub repo
FE-020 | Example story gallery | Medium | S | Improves first-run experience
FE-033 | OpenAPI / Swagger docs | Low | S | Helps API consumers quickly
FE-035 | Architecture diagram in README | Medium | S | Better onboarding for new contributors
FE-015 | Flaky test detection | Low | S | Small reliability boost